**4. Sprint Planning:**

**Project Duration: 6 Weak**

**Number of Total Sprints: 6 Sprint**

**Duration of Single Sprint: 5Days in 1 Week**

**Working Hour (in a Day): 8 Hours**

**Working Hours For 1 Sprint:**

Working hours for one member: 8H\*5D = 40 hours.

Total Working hours for Five members in one sprint: 40\*5 = 200 hours.

Total working hours in the whole project: 200\*6 = 1200 hours.

**Actual Working Hours For 1 Sprint:**

Actual working hours for one member = 6\*5 = 30 hours.

Actual working hours of all (5) members total in one sprint = 5\*30 = 150 hours.

Actual total working hours in the whole project = 150\*6 = 900 hours.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task Name** | **Story Points** | **Start Date** | **End Date** | **Duration** | **Status** |
| **Sprint-1** | 18 | 13.09.2020 | 19.09.2020 | 7 Days | Complete |
| SharePoint Configuration | 5 | 14.09.2020 | 15.09.2020 | 2 | Done |
| Home Page Developing | 13 | 15.09.2020 | 18.09.2020 | 3 | Done |
| **Sprint-2** | 21 | 20.09.2020 | 26.09.2020 | 7 Days | Complete |
| Study Page with Courses | 13 | 21.09.2020 | 23.09.2020 | 3 | Done |
| Alumni Page Development | 8 | 23.09.2020 | 25.09.2020 | 2 | Done |
| **Sprint-3** | 21 | 27.09.2020 | 03.10.2020 | 7 Days | Complete |
| Deal with Enquires Page | 21 | 28.09.2020 | 02.10.2020 | 5 | Done |
| **Sprint-4** | 21 | 04.10.2020 | 10.10.2020 | 7 Days | Complete |
| Develop Research Page | 8 | 05.10.2020 | 07.10.2020 | 2 | Done |
| News Page Development | 13 | 07.10.2020 | 09.10.2020 | 3 | Done |
| **Sprint-5** | 21 | 11.10.2020 | 17.10.2020 | 7 Days | Complete |
| Developing About Page | 13 | 12.10.2020 | 14.10.2020 | 3 | Done |
| About the School/College Page Development | 8 | 15.10.2020 | 16.10.2020 | 2 | Done |
| **Sprint-6** | 21 | 18.10.2020 | 24.10.2020 | 7 Days | Complete |
| Contact Page Development | 8 | 19.10.2020 | 20.10.2020 | 2 | Done |
| Developing Coronavirus Page | 13 | 21.10.2020 | 23.10.2020 | 3 | Done |
|  |  |  |  |  |  |